## A3 Verkefni - Sniðmát (2)
Title: Communication pathways regarding neonatal | Date: | 2. maí 2022 | Project team: Jóhanna Rut Óskarsdóttir hjúkrunarfræðingur, Ella Björg Rögnvaldsóttir ljósmóðir, Sunna María ljósmóðir
Supervisor: Berglind Jónsdóttir |  |  |  |  | Project lead (resident): | Helga Þórunn og Hrafn Hlíðdal
Aim statement (What are we trying to accomplish?) |  |  | 1 | Measures (How will we know a change is an improvement?) (list measures) |  |  |  |  | 4
We want to decrease non-urgent phone calls from Meðgöngu- og sængurlegudeild 22A and Fæðingarvakt 23B by 30% before 29th of April because it can interrupt urgent care and work on the ward without lengthening the time from contact to residents’ reaction. |  |  |  | Count all phone calls received by the neonatal resident each 24 hours from 08:00 to 08:00 the next day. Then filter out the urgent phone calls.
Measure the time it takes from a phone call or a message to be recieved until the resident reacts on it and starts working on the problem
What process(es) are we trying to improve? (process map) |  |  | 2 | Action plan |  |  |  |  | 5
|  |  |  | Action |  |  | By whom | Date | Status
|  |  |  | Process map and fish analysis |  |  | HÞÓ/HHÞ | 03.11.21 | Finished
|  |  |  | Team meeting for planning the project |  |  | Team | 4.11.21 | Finished
|  |  |  | Start measuring phone calls by including other neonatal residents |  |  | HÞÓ/HHÞ | 22.11.21 | Finished
|  |  |  | Baseline results, set up as a run chart started |  |  | HÞÓ/HHÞ | 25.11.21 | Finished
|  |  |  | First results put in the run chart after outcome measurements |  |  | HÞÓ/HHÞ | 23.12.21 | Finished
|  |  |  | Contact Heilsugátt to get a message board to contact residents in NICU |  |  | HHÞ | 11.01.22 | Finished
|  |  |  | Introduction in the wards of 22A and 23B of PDSA1, with a newfound message board directly to the NICU resident. |  |  | JRÓ/EBR&SMHHÞ/HÞÓ | 24.01.22 | Finished
|  |  |  | Start measuring the effect of PDSA1 |  |  | HÞÓ//HHÞ | 31.1.22 | Finished
|  |  |  | Second results put in the run chart |  |  | HÞÓ//HHÞ | 28.2.22 | Finished
|  |  |  | Introduction of PDSA2, with daily check-ins from the NICU resident to 22A |  |  | HÞÓ//HHÞ | 11.2.22 | Finished
|  |  |  | Start measuring the effect of PDSA#2 |  |  | HÞÓ/HHÞ | 14.3.22 | Finished
|  |  |  | Third results, set up as run chart |  |  | HÞÓ/HHÞ | 14.3.22 | Finished
|  |  |  | Introduction of the outcomes of the quality improvement project |  |  | HÞÓ/HHÞ | 12.5.22 | In progress
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  |  | 3 | Results (Run Chart) |  |  |  |  | 6
|  |  |  | Implementation, follow up and lessons learned |  |  |  |  | 7
Change to clinical work and work processes takes a lot more time than anticipated. It is important to maintain the progress made by It was difficult to measure the outcomes since it was dependent on residents that are not in the team to do extra work. That resulted in team members receiving data late and having to constantly remind them to measure outcomes. The message board in Heilsugátt has gotten a status in every day work but the regular visits to the ward need further evaluation if they are to be maintained.

## EXAMPLE
Title: Skráning lífsmarka á bráðamóttöku barna | Date: | 2021-01-01 | Project team: Elín Markúsdóttir, Sandra Salvör og Karitas Gunnarsdóttir , Oddný Kristinsdóttir hjúkrunarfræðingar, Ingibjörg Richter kerfisfræðingur
Supervisor: Viðar Örn Eðvarðsson |  |  |  |  | Project lead (resident): | Urður Jónsdóttir og Kristín Júlía Erlingsdóttir
Aim statement (What are we trying to accomplish?) |  |  | 1 | Meaures (How will we know a change is an improvement?) (list measures) |  |  |  |  | 4
Increase the measurement and recording of full vital signs upon presentation to the pediatric emergency department. Full vital signs are defined as heart rate, oxygen saturation, temperature, blood pressure and respiratory rate. |  |  |  | Prepare guidelines to define and standardize which vital signs should be taken at presentation to the PED. To encourage adherence to these guidelines we will be making changes to Heilsugátt so that missing vital signs are flagged and more visible to those working at each time.
What process(es) are we trying to improve? (process map) |  |  | 2 | Action plan |  |  |  |  | 5
|  |  |  | Action |  |  | By whom | Date | Status
|  |  |  | Process map and fishboe analysis |  |  | KJE/UJ | nov.21 | Finished
|  |  |  | Asseble project team |  |  | KJE/UJ/VÖE | nov.21 | Finished
|  |  |  | Start conversation within the ED |  |  | KG/OK | 2021-11-01 | Finished
|  |  |  | Baseline results, set up as run chart |  |  | KJE | 2021-11-01 | Finished
|  |  |  | First results after conversation started |  |  | KJE/UJ | 2021-12-01 | Finished
|  |  |  | Prepare guidlines |  |  | KJE/UJ | 2021-02-01 | Finished
|  |  |  | PDSA #1: Guidlines official and available |  |  | KJE/UJ/KG/OK | 2021-03-10 | Finished
|  |  |  | Guidlines introduced |  |  | KG/OK | 2021-04-12 | Finished
|  |  |  | Second results, set up as run chart |  |  | KJE/UJ | 2021-04-01 | Finished
|  |  |  | PDSA #2: PEWS |  |  | KG/OK | 2021-05-01 | in progress
|  |  |  | Third results, set up as run chart |  |  | KJE/UJ | 2021-05-01 | in progress
|  |  |  | PDSA #3: Visible on heilsugátt % of patients with full vital signs last 24hrs |  |  | IR | 2021-05-01 | in progress
|  |  |  | Fourth results, set up as run chart |  |  | KJE/UJ | 2021-06-01 | in progress
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  |  | 3 | Results (Run Chart) |  |  |  |  | 6
|  |  |  | Implementation, follow up and lessons learned |  |  |  |  | 7
We are still waiting on the main changes to Heilsugátt and will hopefully see more improvement once they are implemented. Changes take a lot more time than expected. We will analyze further after all changes have been made.